## Oct 24 to Oct 25
Works reference number | Road/Street | Area | USRN | Works location | Works location description | Promoter | Proposed start date | Proposed end date | Total works duration | Activity type | Description of work | Works category | Traffic management type | Footway closure | Work status | Permit reference number | Actual start date | Actual end date | Footpath closure | Working day duration
AY0093023371 | AIR BALLOON ROAD | ST GEORGE | 4525213 | Footway | o/s 90 | BRISTOL WATERWORKS COMPANY | 2024-10-18 | 2024-10-22 | 3 Working days. 5 Calendar days | Utility repair and maintenance works | Repair leaking inlet - Losing 100lph | Minor | Some carriageway incursion | No | Works completed | AY0093023371-01 | 2024-10-18 13:48 | 2024-10-22 10:42 | No | 3
QF00492289444 | AIR BALLOON ROAD | ST GEORGE | 4525213 | Footway, Carriageway | From no. 81 to Troopers Hill Road junction | BRISTOL CITY COUNCIL | 2024-10-28 | 2024-12-02 | 26 Working days. 36 Calendar days | Highway improvement works | Installing new tactile crossing, resurfacing, replacing the permanent signals, refreshing road markings | Major | Road closure | Yes, an alternative route will be provided | Works completed | QF00492289444-02 | 2024-10-28 09:30 | 2024-12-02 15:20 | No | 26
QF00870723675 | AIR BALLOON ROAD | ST GEORGE | 4525213 | Footway | o/s 90 | BRISTOL CITY COUNCIL | 2024-11-11 | 2024-11-13 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | install supply cable | Minor | No carriageway incursion | No | Works completed | QF00870723675-01 | 2024-11-12 09:30 | 2024-11-12 12:00 | No | 1
BC004WG3DR20B | AIR BALLOON ROAD | ST GEORGE | 4525213 | Footway | o/s 20h Air Balloon Road | BT | 2024-12-30 | 2024-12-31 | 1 Working days. 1 Calendar days | Utility repair and maintenance works | Maintenance dig to clear duct blockage in footway in existing telecoms ducting. | Minor | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | BC004WG3DR20B-01 | 2024-12-30 09:24 | 2024-12-30 09:49 | No | 1
D201724810794 | AIR BALLOON ROAD | ST GEORGE | 4525213 | Footway | o/s Methodist Church | Netomnia Limited | 2025-03-31 | 2025-04-01 | 2 Working days. 2 Calendar days | Utility asset works | Clear blockage in footway | Minor | No carriageway incursion | No | Works completed | D201724810794-01 | 2025-03-31 14:59 | 2025-04-01 16:30 | No | 2
D201724810794 | AIR BALLOON ROAD | ST GEORGE | 4525213 | Footway | o/s Methodist Church | Netomnia Limited | 2025-04-07 | 2025-04-07 | 1 Working days. 1 Calendar days | Permanent reinstatement | Make Interim Reinstatement Perm | Minor | No carriageway incursion | No | Works completed | D201724810794-02 | 2025-04-07 09:30 | 2025-04-07 10:18 | No | 1
BC008OGEA17846005CVSB | AIR BALLOON ROAD | ST GEORGE | 4525213 | Footway, Carriageway | Outside of No5 to No.36, Air Balloon Road, Bristol, BS5 8LS | BT | 2025-09-09 | 2025-09-09 | 1 Working days. 1 Calendar days | Utility asset works | To provide a safe working area for engineers to access EXISTING footway box(s) to provide ducting for a customer. 2 way TL,TUSC (AB) Boards in use, Temporary Footway. 1 working day 0900-1700 ** Excavation in footway ** | Minor | Two-way signals | Yes, a pedestrian walkway will be provided | Works completed | BC008OGEA17846005CVSB-01 | 2025-09-09 09:17 | 2025-09-09 13:57 | No | 1
NK110ANSL198676 | AVONVALE ROAD | REDFIELD | 4532187 | Footway | O/S 186 Avonvale Road to O/S Ashmead House & from 201 avonvale rd to 215 avonvale rd | VIRGIN MEDIA | 2024-10-17 | 2024-10-18 | 1 Working days. 1 Calendar days | Utility asset works | Extend duct 8m in F/W and clear Clear blockages | Minor | Some carriageway incursion | Yes, an alternative route will be provided | Works completed | NK110ANSL198676-03 | 2024-10-18 13:27 | 2024-10-18 14:20 | No | 1
QF00470162601 | AVONVALE ROAD | REDFIELD | 4532187 | Footway, Carriageway | From Marsh Lane jct to Beam Street jct | BRISTOL CITY COUNCIL | 2024-11-19 | 2024-11-19 | 1 Working days. 1 Calendar days | Highway improvement works | Installation of planters and bus gate to restrict vehicle access | Minor | Road closure | No | Works completed | QF00470162601-01 | 2024-11-19 08:30 | 2024-11-19 15:00 | No | 1
LN0142481010 | AVONVALE ROAD | REDFIELD | 4532187 | Footway | Outside 193 Avonvale Rd | National Grid Electricity Distribution (South West) | 2024-11-24 | 2024-11-29 | 5 Working days. 6 Calendar days | Utility repair and maintenance works | Urgent excavation in highway to locate and repair LV cable fault. | Immediate - urgent | Give and take | Yes, an alternative route will be provided | Works completed | LN0142481010-01 | 2024-11-24 10:30 | 2024-11-29 14:30 | No | 5
LN0142481634A | AVONVALE ROAD | REDFIELD | 4532187 | Footway, Carriageway | To the side of 185 | National Grid Electricity Distribution (South West) | 2024-11-28 | 2024-12-04 | 5 Working days. 7 Calendar days | Utility repair and maintenance works | Urgent excavation in highway to locate and repair LV cable fault. | Immediate - urgent | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | LN0142481634A-01 | 2024-11-28 10:00 | 2024-12-04 10:02 | No | 5
LN0142481632 | AVONVALE ROAD | REDFIELD | 4532187 | Footway | Outside 191 | National Grid Electricity Distribution (South West) | 2024-11-28 | 2024-12-04 | 5 Working days. 7 Calendar days | Utility repair and maintenance works | Urgent excavation in highway to locate and repair LV cable fault. | Immediate - urgent | Some carriageway incursion | Yes, an alternative route will be provided | Works completed | LN0142481632-01 | 2024-11-28 10:00 | 2024-12-04 10:03 | No | 5
QF01144149638 | AVONVALE ROAD | REDFIELD | 4532187 | Footway, Carriageway | Approximately 15m from Church Road towards south on Avonvale Road | BRISTOL CITY COUNCIL | 2025-01-14 | 2025-01-14 | 1 Working days. 1 Calendar days | Highway improvement works | Retrofit - Traffic signals pole and equipment replacement | Minor | Multi-way signals | No | Works completed | QF01144149638-01 | 2025-01-14 09:30 | 2025-01-14 15:30 | No | 1
QF00470162601 | AVONVALE ROAD | REDFIELD | 4532187 | Footway, Carriageway | From Marsh Lane jct to Beam Street jct | BRISTOL CITY COUNCIL | 2025-01-27 | 2025-01-27 | 1 Working days. 1 Calendar days | Highway improvement works | Installation of planters and bus gate to restrict vehicle access | Minor | Road closure | No | Works completed | QF00470162601-02 | 2025-01-27 09:00 | 2025-01-27 14:00 | No | 1
XY213001004857656 | AVONVALE ROAD | REDFIELD | 4532187 | Footway, Carriageway | OPP 104 | WALES AND WEST UTILITIES LTD | 2025-02-03 | 2025-02-10 | 5 Working days. 5 Calendar days | Utility repair and maintenance works | TRACE AND REPAIR GAS ESCAPE AND PERMANENTLY REINSTATE WHERE POSSIBLE. | Immediate - emergency | Road closure | Yes, a pedestrian walkway will be provided | Works completed | XY213001004857656-01 | 2025-02-03 17:55 | 2025-02-07 14:58 | No | 5
AY0093031906 | AVONVALE ROAD | REDFIELD | 4532187 | Footway | o/s 183 | BRISTOL WATERWORKS COMPANY | 2025-03-14 | 2025-03-18 | 3 Working days. 5 Calendar days | Utility repair and maintenance works | Repair leaking stoptap - Losing 20lph | Minor | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | AY0093031906-05 | 2025-03-14 13:00 | 2025-03-18 13:40 | No | 3
QF00519130105 | AVONVALE ROAD | REDFIELD | 4532187 | Carriageway | From its junction with Oxford Street to its junction Baden Road | BRISTOL CITY COUNCIL | 2025-03-26 | 2025-03-26 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | CAT2 Pothole repairs | Immediate - urgent | Road closure | No | Works completed | QF00519130105-01 | 2025-03-26 09:30 | 2025-03-26 15:30 | No | 1
NK110ANSL236856 | AVONVALE ROAD | REDFIELD | 4532187 | Footway | OUTSIDE 138a avonvale road | VIRGIN MEDIA | 2025-05-28 | 2025-05-30 | 3 Working days. 3 Calendar days | Utility asset works | CLEAR BLOCKAGES | Minor | Some carriageway incursion | Yes, an alternative route will be provided | Works completed | NK110ANSL236856-01 | 2025-05-28 14:14 | 2025-05-30 15:58 | No | 3
PG10763684326001 | AVONVALE ROAD | REDFIELD | 4532187 | Carriageway | From Junct with Cooperage Road t o Junct with Avon Park | WESSEX WATER | 2025-09-29 | 2025-09-29 | 1 Working days. 1 Calendar days | Utility repair and maintenance works | Section 81/Defect - Repair/Replace Cover & Frame | Minor | Road closure | No | Works completed | PG10763684326001-01 | 2025-09-29 09:30 | 2025-09-29 14:45 | No | 1
BC008FAA6088MCR0AR4A | BARROW ROAD | LAWRENCE HILL | 4538754 | Footway | Working from corner of Barton Hill Road to corner of Robert Street | BT | 2025-02-17 | 2025-02-20 | 4 Working days. 4 Calendar days | Utility asset works | Access to Openreach underground equipment. Night working | Standard | No carriageway incursion | No | Works completed | BC008FAA6088MCR0AR4A-01 | 2025-02-17 16:17 | 2025-02-20 06:30 | No | 4
BC412-BWDOSA-WG5JLL7X | BARROW ROAD | LAWRENCE HILL | 4538754 | Footway, Carriageway | opp 87 to opp jnct of robert street | BT | 2025-06-06 | 2025-06-10 | 3 Working days. 5 Calendar days | Utility asset works | works to lay approx 50m of duct | Minor | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | BC412-BWDOSA-WG5JLL7X-01 | 2025-06-06 09:10 | 2025-06-10 20:14 | No | 3
BC412-BWDOSA-A-WG5JLL7X | BARROW ROAD | LAWRENCE HILL | 4538754 | Carriageway | opp 85 to opp 87 | BT | 2025-06-18 | 2025-06-20 | 1 Working days. 1 Calendar days | Utility asset works | works to lay approx 15m of duct | Minor | Some carriageway incursion | No | Works completed | BC412-BWDOSA-A-WG5JLL7X-01 | 2025-06-18 18:40 | 2025-06-18 23:58 | No | 1
PG10763619814001 | BARROW ROAD | LAWRENCE HILL | 4538754 | Footway | Entrance to Barrow Court | WESSEX WATER | 2025-07-22 | 2025-07-24 | 1 Working days. 1 Calendar days | Utility repair and maintenance works | Repair/Replace Manhole Cover/Frame/Chamber - Repair Dangerous Cover | Immediate - urgent | Some carriageway incursion | Yes, an alternative route will be provided | Works completed | PG10763619814001-01 | 2025-07-22 16:40 | 2025-07-22 20:00 | No | 1
QF00502611270 | BARTON HILL ROAD | ST PHILIPS | 4561765 | Carriageway | Between junction with Queen Ann Road and Church Street | BRISTOL CITY COUNCIL | 2021-08-05 | 2021-08-07 | 2 Working days. 3 Calendar days | Highway repair and maintenance works | Sinkhole investigation and repair. | Immediate - emergency | Road closure | No | Works in progress | QF00502611270-01 | 2021-08-05 09:00 |  | No | 2
NK110ANSL206614 | BARTON HILL ROAD | ST PHILIPS | 4561765 | Footway | Outside 65 BARTON HILL ROAD BRISTOL BS5 0AP | VIRGIN MEDIA | 2024-10-18 | 2024-10-21 | 1 Working days. 1 Calendar days | Utility asset works | INSTALL TEE IN FOOTWAY (NEW CUSTOMER CONNECTION) | Minor | No carriageway incursion | No | Works completed | NK110ANSL206614-01 | 2024-10-18 13:39 | 2024-10-18 14:12 | No | 1
QF00565350540 | BARTON HILL ROAD | ST PHILIPS | 4561765 | Carriageway | From number 70 to its junction with Gullybrook Lane | BRISTOL CITY COUNCIL | 2024-10-23 | 2024-10-23 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | CAT2 Pothole Repairs | Minor | Road closure | No | Works completed | QF00565350540-01 | 2024-10-23 06:54 | 2024-10-23 10:58 | No | 1
NK110ANSL221047 | BARTON HILL ROAD | ST PHILIPS | 4561765 | Footway | outside FLAT 7 65 BARTON HILL ROAD BRISTOL BS5 0AP | VIRGIN MEDIA | 2025-02-03 | 2025-02-04 | 1 Working days. 1 Calendar days | Utility asset works | INSTALL TEE IN FOOTWAY (NEW CUSTOMER CONNECTION) | Minor | No carriageway incursion | No | Works completed | NK110ANSL221047-01 | 2025-02-03 09:28 | 2025-02-03 10:23 | No | 1
BC008FAA6088MCR0AR3 | BARTON HILL ROAD | ST PHILIPS | 4561765 | Footway | Corner of Ducie Road to corner of Barrow Road | BT | 2025-02-17 | 2025-02-20 | 4 Working days. 4 Calendar days | Utility asset works | Access to Openreach underground equipment. Night working | Standard | No carriageway incursion | No | Works completed | BC008FAA6088MCR0AR3-02 | 2025-02-17 16:16 | 2025-02-20 06:30 | No | 4
QF00892674746 | BARTON HILL ROAD | ST PHILIPS | 4561765 | Footway | From j/o Barrow Road to Opp Gullybrook Lane | BRISTOL CITY COUNCIL | 2025-03-10 | 2025-03-17 | 5 Working days. 6 Calendar days | Highway repair and maintenance works | Repair cable fault | Standard | Multi-way signals | Yes, an alternative route will be provided | Works completed | QF00892674746-01 | 2025-03-10 09:30 | 2025-03-15 14:30 | No | 5
BC412SWONSAWG1NG38Y | BARTON HILL ROAD | ST PHILIPS | 4561765 | Footway | O/S 65 | BT | 2025-04-29 | 2025-05-01 | 2 Working days. 2 Calendar days | Utility asset works | Excavate to lay approx. 8mtrs of duct. | Minor | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | BC412SWONSAWG1NG38Y-01 | 2025-04-29 12:04 | 2025-04-30 15:36 | No | 2
AY0073075728 | BARTON HILL ROAD | ST PHILIPS | 4561765 | Footway | OS/ 76 | BRISTOL WATERWORKS COMPANY | 2025-09-25 | 2025-09-30 | 4 Working days. 6 Calendar days | Utility repair and maintenance works | Repair leaking stop tap | Standard | Some carriageway incursion | Yes, an alternative route will be provided | Works completed | AY0073075728-01 | 2025-09-25 08:34 | 2025-09-30 10:00 | No | 4
QF00424726462 | BEAUFORT ROAD | ST GEORGE | 4528931 | Footway, Carriageway | From Blackswarth Road junction to Northcote Road junction | BRISTOL CITY COUNCIL | 2024-10-30 | 2024-10-31 | 2 Working days. 2 Calendar days | Highway improvement works | Installation of planters and bollards to restrict vehicle access | Minor | Road closure | No | Works completed | QF00424726462-01 | 2024-10-30 09:00 | 2024-10-31 15:30 | No | 2
AY0092981749 | BEAUFORT ROAD | ST GEORGE | 4528931 | Carriageway | o/s 93-95 | BRISTOL WATERWORKS COMPANY | 2024-12-10 | 2024-12-13 | 4 Working days. 4 Calendar days | Utility repair and maintenance works | Exchange fire hydrant | Standard | Some carriageway incursion | No | Works completed | AY0092981749-04 | 2024-12-10 09:25 | 2024-12-13 15:10 | No | 4
QF00432002769 | BEAUFORT ROAD | ST GEORGE | 4528931 | Carriageway | Opposite 65 Beaufort Road | BRISTOL CITY COUNCIL | 2025-02-06 | 2025-02-07 | 2 Working days. 2 Calendar days | Highway improvement works | Bollard installation | Minor | Some carriageway incursion | No | Works completed | QF00432002769-01 | 2025-01-30 09:00 | 2025-01-30 12:00 | No | 2
AY0093044508 | BEAUFORT ROAD | ST GEORGE | 4528931 | Footway, Carriageway | Outside 139 | BRISTOL WATERWORKS COMPANY | 2025-02-03 | 2025-02-07 | 5 Working days. 5 Calendar days | Utility repair and maintenance works | Separation of supply | Standard | Give and take | Yes, an alternative route will be provided | Works completed | AY0093044508-01 | 2025-02-03 10:58 | 2025-02-07 12:05 | No | 5
QF00461982037 | BEAUFORT ROAD | ST GEORGE | 4528931 | Carriageway | Opposite 65 Beaufort Road | BRISTOL CITY COUNCIL | 2025-02-25 | 2025-02-27 | 21 Working days. 29 Calendar days | Highway improvement works | Cycle hanger installation | Minor | Some carriageway incursion | No | Works completed | QF00461982037-01 | 2025-02-26 08:30 | 2025-03-26 12:00 | No | 21
D201786985407 | BELL HILL ROAD | ST GEORGE | 4547488 | Footway, Carriageway | o/s 129 - o/s 149 & o/s 140 - o/s 162 | Netomnia Limited | 2024-10-06 | 2024-10-08 | 1 Working days. 2 Calendar days | Utility asset works | Clear blockage in footway and open cw chamber | Minor | Multi-way signals | Yes, a pedestrian walkway will be provided | Works completed | D201786985407-03 | 2024-10-06 09:00 | 2024-10-07 14:23 | No | 1
NK110ANSL203740 | BELL HILL ROAD | ST GEORGE | 4547488 | Footway | OUTSIDE 162 bell hill road | VIRGIN MEDIA | 2025-01-23 | 2025-01-27 | 1 Working days. 1 Calendar days | Utility asset works | new chamber & 2m of duct for Doctors | Minor | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | NK110ANSL203740-06 | 2025-01-24 17:03 | 2025-01-24 17:46 | No | 1
NK110ANSL203740 | BELL HILL ROAD | ST GEORGE | 4547488 | Footway | OUTSIDE 162 BELL HILL ROAD BRISTOL BS5 7NF | VIRGIN MEDIA | 2025-03-01 | 2025-03-02 | 0 Working days. 1 Calendar days | Utility asset works | Install Chamber and ducting for Doctors surgery | Minor | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | NK110ANSL203740-09 | 2025-03-02 13:15 | 2025-03-02 14:22 | No | 0
BC008OGEAA0483230 | BELL HILL ROAD | ST GEORGE | 4547488 | Carriageway | 3 Bell Hill Road Bristol BS5 7LT | BT | 2025-06-24 | 2025-06-24 | 1 Working days. 1 Calendar days | Utility repair and maintenance works | to provide a safe working area for engineers to access telegraph poles in order to restore fibre overhead cabling and restore customer service. 4 way lights + Footway closure , switch off . 1 working day 09:30 - 15:30 ** No Excavation ** | Immediate - urgent | Multi-way signals | Yes, a pedestrian walkway will be provided | Works completed | BC008OGEAA0483230-01 | 2025-06-24 09:30 | 2025-06-24 15:30 | No | 1
AY0093090443 | BELL HILL ROAD | ST GEORGE | 4547488 | Footway | From outside 157 Clouds Hill Road to outside 14 Bell Hill Road. | BRISTOL WATERWORKS COMPANY | 2025-07-15 | 2025-07-17 | 3 Working days. 3 Calendar days | Utility repair and maintenance works | Repair leaking stop tap - 100LPH | Minor | Multi-way signals | Yes, a pedestrian walkway will be provided | Works completed | AY0093090443-01 | 2025-07-15 09:27 | 2025-07-17 16:54 | No | 3
BC00810SEPSS1QBP32 | BELL HILL ROAD | ST GEORGE | 4547488 | Carriageway | 135 BELL HILL ROAD BRISTOL BS5 7NQ | BT | 2025-09-09 | 2025-09-10 | 2 Working days. 2 Calendar days | Utility repair and maintenance works | Urgent access for Engineers to work in Underground structure to repair cables customer without service - fault ref SS1QBP32 | Immediate - urgent | Two-way signals | No | Works completed | BC00810SEPSS1QBP32-01 | 2025-09-09 21:00 | 2025-09-10 | No | 2
BC00510SEPSS1QBP32 | BELL HILL ROAD | ST GEORGE | 4547488 | Carriageway | 135 BELL HILL ROAD BRISTOL BS5 7NQ | BT | 2025-09-09 | 2025-09-10 | 2 Working days. 2 Calendar days | Utility repair and maintenance works | Urgent access for Engineers to work in Underground structure to repair cables customer without service - fault ref SS1QBP32 | Immediate - urgent | Two-way signals | No | Works completed | BC00510SEPSS1QBP32-01 | 2025-09-09 21:00 | 2025-09-10 | No | 2
PG10763529370001 | BELL HILL ROAD | ST GEORGE | 4547488 | Carriageway | 22 Bell Hill-Junct Whiteway Road & Clouds Hill Road | WESSEX WATER | 2025-09-23 | 2025-09-24 | 2 Working days. 2 Calendar days | Utility repair and maintenance works | Section 81/Defect | Minor | Multi-way signals | No | Works completed | PG10763529370001-03 | 2025-09-23 19:29 | 2025-09-24 00:56 | No | 2
AY0073076296 | BELL HILL ROAD | ST GEORGE | 4547488 | Footway | O/S 51 | BRISTOL WATERWORKS COMPANY | 2025-09-24 | 2025-09-26 | 2 Working days. 4 Calendar days | Utility repair and maintenance works | Repair leaking stop tap | Minor | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | AY0073076296-01 | 2025-09-25 14:48 | 2025-09-28 11:22 | No | 2
XY212001005053917 | BELL HILL ROAD | ST GEORGE | 4547488 | Footway, Carriageway | O/S 24 | WALES AND WEST UTILITIES LTD | 2025-09-30 | 2025-10-06 | 5 Working days. 7 Calendar days | Utility repair and maintenance works | TRACE AND REPAIR GAS ESCAPE AND PERMANENTLY REINSTATE WHERE POSSIBLE. | Immediate - emergency | Some carriageway incursion | Yes, an alternative route will be provided | Works completed | XY212001005053917-01 | 2025-09-30 02:10 | 2025-10-06 14:45 | No | 5
AY0092997843 | BLACKSWARTH ROAD | ST GEORGE | 4530525 | Footway | FROM 2 TO 15 | BRISTOL WATERWORKS COMPANY | 2024-10-29 | 2024-10-30 | 2 Working days. 2 Calendar days | Utility repair and maintenance works | HYDRANT REPLACEMENT | Minor | Two-way signals | Yes, a pedestrian walkway will be provided | Works completed | AY0092997843-02 | 2024-10-29 11:30 | 2024-10-30 17:00 | No | 2
XY211001004817779 | BLACKSWARTH ROAD | ST GEORGE | 4530525 | Footway, Carriageway, Verge | O/S SATELLITE HOUSE 160 | WALES AND WEST UTILITIES LTD | 2024-12-20 | 2024-12-30 | 1 Working days. 3 Calendar days | Utility repair and maintenance works | TRACE AND REPAIR GAS ESCAPE AND PERMANENTLY REINSTATE WHERE POSSIBLE. | Immediate - emergency | Some carriageway incursion | No | Works completed | XY211001004817779-01 | 2024-12-20 10:25 | 2024-12-22 21:41 | No | 1
XY212004000192156_01 | BLACKSWARTH ROAD | ST GEORGE | 4530525 | Footway, Carriageway | ADJ TO 1 LEWIN STREET | WALES AND WEST UTILITIES LTD | 2025-02-20 | 2025-02-26 | 5 Working days. 7 Calendar days | Utility repair and maintenance works | LAY NEW SERVICE 1M PUBLIC | Standard | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | XY212004000192156_01-01 | 2025-02-20 10:25 | 2025-02-24 14:00 | No | 5
QF01205508576 | BLACKSWARTH ROAD | ST GEORGE | 4530525 | Carriageway | Entire length of Blackswarth Road | BRISTOL CITY COUNCIL | 2025-03-01 | 2025-03-03 | 1 Working days. 3 Calendar days | Highway repair and maintenance works | Pothole repair and surfacing | Minor | Two-way signals | No | Works completed | QF01205508576-01 | 2025-03-01 08:00 | 2025-03-03 15:30 | No | 1
QF01205508576 | BLACKSWARTH ROAD | ST GEORGE | 4530525 | Carriageway | From Fireclay Road junction to Crews Hole Road junction | BRISTOL CITY COUNCIL | 2025-03-23 | 2025-03-23 | 0 Working days. 1 Calendar days | Highway repair and maintenance works | Pothole repair and surfacing | Minor | Road closure | No | Works completed | QF01205508576-02 | 2025-03-23 08:00 | 2025-03-23 17:00 | No | 0
AY0093053375 | BLACKSWARTH ROAD | ST GEORGE | 4530525 | Carriageway | From 76 To Junction with Grindell Road | BRISTOL WATERWORKS COMPANY | 2025-04-01 | 2025-04-03 | 3 Working days. 3 Calendar days | Utility repair and maintenance works | Burst Main - Losing 1500lph | Minor | Multi-way signals | No | Works completed | AY0093053375-04 | 2025-04-01 12:15 | 2025-04-03 17:10 | No | 3
QF01117624018 | BLACKSWARTH ROAD | ST GEORGE | 4530525 | Carriageway | Approximately from Derby Street to Lewin Street on Blackswarth Road | BRISTOL CITY COUNCIL | 2025-04-14 | 2025-04-15 | 2 Working days. 2 Calendar days | Highway repair and maintenance works | Traffic signal detection repair in the road | Minor | Two-way signals | No | Works completed | QF01117624018-01 | 2025-04-14 20:00 | 2025-04-15 02:00 | No | 2
QF00572770707 | BLACKSWARTH ROAD | ST GEORGE | 4530525 | Carriageway | From its junction with Church Road to its junction with Crews Hole Road | BRISTOL CITY COUNCIL | 2025-05-11 | 2025-05-11 | 0 Working days. 1 Calendar days | Statutory Infrastructure Works | Surface dressing (SD) | Minor | Road closure | No | Works planned | QF00572770707-01 | 2025-05-11 08:00 | 2025-05-11 18:00 | No | 0
QF00572770707 | BLACKSWARTH ROAD | ST GEORGE | 4530525 | Carriageway | From its junction with Church Road to its junction with Crews Hole Road | BRISTOL CITY COUNCIL | 2025-06-03 | 2025-06-06 | 4 Working days. 4 Calendar days | Statutory Infrastructure Works | Road Marking reinstatement following Surface Dressing | Standard | Stop/go boards | No | Works planned | QF00572770707-03 | 2025-06-03 09:30 | 2025-06-06 15:30 | No | 4
AY0093115546 | BLACKSWARTH ROAD | ST GEORGE | 4530525 | Carriageway | From o/s 80 to o/s 84 | BRISTOL WATERWORKS COMPANY | 2025-09-15 | 2025-09-19 | 5 Working days. 5 Calendar days | Utility repair and maintenance works | Repair leaking service pipe - 3000LPH | Immediate - urgent | Multi-way signals | No | Works completed | AY0093115546-01 | 2025-09-15 12:29 | 2025-09-19 17:30 | No | 5
AY0092889394 | CHALKS ROAD | ST GEORGE | 4544953 | Footway | from outside 40 to outside 30 | BRISTOL WATERWORKS COMPANY | 2025-07-22 | 2025-07-23 | 1 Working days. 1 Calendar days | Utility repair and maintenance works | dangerous cover | Minor | Two-way signals | Yes, a pedestrian walkway will be provided | Works completed | AY0092889394-02 | 2025-07-22 19:00 | 2025-07-22 21:03 | No | 1
A2101ENV9901-JW01 | CHALKS ROAD | ST GEORGE | 4544953 | Footway, Carriageway | Chalks Road approx. outside NO56 to to approx. 31m from Tintern Ave | mua Electricity Limited | 2025-07-29 | 2025-08-08 | 4 Working days. 4 Calendar days | New service connection | Excavation to lay a LV cable to install an EV charger | Standard | Two-way signals | Yes, an alternative route will be provided | Works completed | A2101ENV9901-JW01-04 | 2025-07-29 08:20 | 2025-08-01 16:45 | No | 4
A2101ENV9901-JW01 | CHALKS ROAD | ST GEORGE | 4544953 | Footway | Chalks Road full works from NO 53 Chalks road to No 11 Chalks Road | mua Electricity Limited | 2025-10-03 | 2025-10-06 | 2 Working days. 4 Calendar days | Utility asset works | Excavation to lay a LV cable to install an EV charger | Minor | Two-way signals | Yes, an alternative route will be provided | Works completed | A2101ENV9901-JW01-06 | 2025-10-03 07:30 | 2025-10-06 19:45 | No | 2
XY212008000186641 | CHURCH ROAD | REDFIELD | 4525712 | Footway, Carriageway | O/S 263 CHURCH ROAD | WALES AND WEST UTILITIES LTD | 2024-10-01 | 2024-10-03 | 3 Working days. 3 Calendar days | Utility repair and maintenance works | ISOLATING SERVICE 1M PUBLIC | Minor | Some carriageway incursion | No | Works completed | XY212008000186641-05 | 2024-10-01 13:08 | 2024-10-03 13:35 | No | 3
QF01108025756 | CHURCH ROAD | REDFIELD | 4525712 | Carriageway | Approximately between 163 and 189 Church Road | BRISTOL CITY COUNCIL | 2024-10-09 | 2024-10-09 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | Traffic signals detection repair in the road | Minor | Two-way signals | No | Works completed | QF01108025756-01 | 2024-10-09 19:00 | 2024-10-09 23:00 | No | 1
QF01135216728 | CHURCH ROAD | REDFIELD | 4525712 | Carriageway | Approx between Lyppiatt Road and Roseberry Park | BRISTOL CITY COUNCIL | 2024-10-15 | 2024-10-15 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | RTC Traffic signals pole and equipment replacement on mast arm | Minor | Two-way signals | No | Works completed | QF01135216728-01 | 2024-10-15 09:30 | 2024-10-15 15:00 | No | 1
QF01172418069 | CHURCH ROAD | REDFIELD | 4525712 | Carriageway | Approx between 169 and 181 Church Road | BRISTOL CITY COUNCIL | 2024-10-15 | 2024-10-15 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | RTC Traffic signals pole and equipment replacement on mast arm | Minor | Two-way signals | No | Works completed | QF01172418069-01 | 2024-10-15 09:30 | 2024-10-15 15:00 | No | 1
QF01191560487 | CHURCH ROAD | ST GEORGE | 4567925 | Footway | Approximately 10 m from 361 Church Road opposite to 294 Church Road | BRISTOL CITY COUNCIL | 2024-12-05 | 2024-12-05 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | RTC Traffic signals pole and equipment replacement | Minor | No carriageway incursion | No | Works completed | QF01191560487-01 | 2024-12-05 09:30 | 2024-12-05 15:00 | No | 1
QF01174234932 | CHURCH ROAD | ST GEORGE | 4567925 | Footway, Carriageway, Verge | Approximately from 338 to 350 Church Road | BRISTOL CITY COUNCIL | 2024-12-17 | 2024-12-17 | 1 Working days. 1 Calendar days | Highway improvement works | Retrofit - Traffic signals pole and equipment replacement | Minor | Multi-way signals | No | Works completed | QF01174234932-01 | 2024-12-17 09:30 | 2024-12-17 14:00 | No | 1
QF01103948985 | CHURCH ROAD | REDFIELD | 4525712 | Footway, Carriageway | Approximately from 209 to 233 Church Road | BRISTOL CITY COUNCIL | 2025-01-14 | 2025-01-14 | 1 Working days. 1 Calendar days | Highway improvement works | Retrofit - Traffic signals pole and equipment replacement | Minor | Multi-way signals | No | Works completed | QF01103948985-01 | 2025-01-14 09:30 | 2025-01-14 15:30 | No | 1
D201754386242 | CHURCH ROAD | REDFIELD | 4525712 | Footway | S/O 157 | Netomnia Limited | 2025-01-23 | 2025-01-27 | 3 Working days. 5 Calendar days | Utility asset works | Clear footway blockage | Minor | No carriageway incursion | No | Works completed | D201754386242-01 | 2025-01-23 09:30 | 2025-01-27 15:30 | No | 3
XY212004000192167_01 | CHURCH ROAD | REDFIELD | 4525712 | Footway, Carriageway | CONTRA FLOW SYSTEM IN USE FROM O/S 217 TO O/S 201 | WALES AND WEST UTILITIES LTD | 2025-02-10 | 2025-02-13 | 3 Working days. 3 Calendar days | Utility repair and maintenance works | LAYING NEW SERVICE 6M PUBLIC | Standard | Contra-flow | Yes, a pedestrian walkway will be provided | Works completed | XY212004000192167_01-02 | 2025-02-10 09:45 | 2025-02-12 17:15 | No | 3
QF01105032884 | CHURCH ROAD | LAWRENCE HILL | 4543033 | Footway, Carriageway | Approximately from Jane Street to Heber Street on Church Road | BRISTOL CITY COUNCIL | 2025-02-14 | 2025-02-14 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | Retrofit - Traffic signal head replacement | Minor | Multi-way signals | No | Works completed | QF01105032884-01 | 2025-02-14 09:30 | 2025-02-14 15:30 | No | 1
XY212004000191205 | CHURCH ROAD | REDFIELD | 4525712 | Footway, Carriageway | BUS LANE CLOSED FROM O/S 239 TO O/S 211 | WALES AND WEST UTILITIES LTD | 2025-03-09 | 2025-03-12 | 3 Working days. 4 Calendar days | Utility repair and maintenance works | LAYING NEW SERVICE 5M PUBLIC | Minor | Lane closure | No | Works completed | XY212004000191205-01 | 2025-03-09 09:22 | 2025-03-12 10:28 | No | 3
AY0093065406 | CHURCH ROAD | REDFIELD | 4525712 | Footway | Adjacent Dove Lane | BRISTOL WATERWORKS COMPANY | 2025-04-03 | 2025-04-07 | 3 Working days. 5 Calendar days | Utility repair and maintenance works | Repair leaking service pipe - Losing 300 LPH. | Immediate - urgent | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | AY0093065406-01 | 2025-04-03 08:45 | 2025-04-07 10:32 | No | 3
LN0782494342A | CHURCH ROAD | LAWRENCE HILL | 4543033 | Footway | ADJ TO NUMBER 8 | National Grid Electricity Distribution (South West) | 2025-04-14 | 2025-04-17 | 4 Working days. 4 Calendar days | New service connection | 1 joint hole in tarmac footway for new supply | Standard | Some carriageway incursion | No | Works completed | LN0782494342A-01 | 2025-04-14 09:44 | 2025-04-17 16:45 | No | 4
BC336-MH-WG6MRH6J | CHURCH ROAD | REDFIELD | 4525712 | Footway, Carriageway | 182 CHURCH ROAD REDFIELD BRISTOL BS5 9HX | BT | 2025-05-12 | 2025-05-17 | 5 Working days. 6 Calendar days | Utility repair and maintenance works | Trail Excavation to ascertain if new Shaft can be installed for Complex Manhole | Standard | Some carriageway incursion | No | Works completed | BC336-MH-WG6MRH6J-01 | 2025-05-12 08:30 | 2025-05-17 16:00 | No | 5
NK110ANSL243816 | CHURCH ROAD | REDFIELD | 4525712 | Footway | outside 91 -101 CHURCH ROAD REDFIELD BRISTOL BS5 9JS | VIRGIN MEDIA | 2025-07-22 | 2025-07-23 | 1 Working days. 1 Calendar days | Utility asset works | TRIAL/WINDOW DIG IN FOOTWAY (NEW CUSTOMER CONNECTION) | Minor | Some carriageway incursion | No | Works completed | NK110ANSL243816-01 | 2025-07-22 11:14 | 2025-07-22 12:37 | No | 1
LN0782508310A | CHURCH ROAD | LAWRENCE HILL | 4543033 | Footway | At junction of Church Road and Cobden Street | National Grid Electricity Distribution (South West) | 2025-07-29 | 2025-08-01 | 4 Working days. 4 Calendar days | New service connection | 1 joint hole in modular footway for new supply | Standard | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | LN0782508310A-01 | 2025-07-29 14:45 | 2025-08-01 16:55 | No | 4
BC336MH-WG0WP13F | CHURCH ROAD | REDFIELD | 4525712 | Footway, Carriageway | 186 Church road to 156 Church road | BT | 2025-08-18 | 2025-10-31 | 54 Working days. 75 Calendar days | Utility repair and maintenance works | Trail excavation to acertain if new MH boxes can be installed & install 2 new & 6 way-duct | Major | Contra-flow | No | Works in progress | BC336MH-WG0WP13F-01 | 2025-08-18 09:51 |  | No | 54
NK110ANSL235126 | CHURCH ROAD | REDFIELD | 4525712 | Footway | Outside 156 and 160 CHURCH ROAD REDFIELD BRISTOL BS5 9HX | VIRGIN MEDIA | 2025-08-20 | 2025-08-21 | 2 Working days. 2 Calendar days | Utility asset works | INSTALL TEE IN FOOTWAY (NEW CUSTOMER CONNECTION) | Minor | No carriageway incursion | Yes, an alternative route will be provided | Works completed | NK110ANSL235126-04 | 2025-08-20 11:24 | 2025-08-20 12:31 | No | 2
BC412-BWDOSA-WGHD6F9M | CHURCH ROAD | ST GEORGE | 4567925 | Footway | o/s 268 | BT | 2025-09-22 | 2025-09-23 | 2 Working days. 2 Calendar days | Utility asset works | Damaged frame and cover , urgent repair required to avoid further deterioration | Immediate - emergency | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | BC412-BWDOSA-WGHD6F9M-01 | 2025-09-22 11:00 | 2025-09-23 16:35 | No | 2
AY0073069884 | CHURCH ROAD | ST GEORGE | 4567925 | Footway | outside 389 | BRISTOL WATERWORKS COMPANY | 2025-09-24 | 2025-09-25 | 2 Working days. 2 Calendar days | Utility repair and maintenance works | EXAMINE STOPTAP O/L TO BOUNDARY FOR LEAK | Minor | Some carriageway incursion | Yes, an alternative route will be provided | Works completed | AY0073069884-01 | 2025-09-24 15:45 | 2025-09-25 17:05 | No | 2
AY0033018835 | CLOUDS HILL ROAD | ST GEORGE | 4545035 | Footway | O/S 116 | BRISTOL WATERWORKS COMPANY | 2024-10-14 | 2024-10-15 | 1 Working days. 1 Calendar days | Utility repair and maintenance works | Install new meter | Minor | Some carriageway incursion | No | Works completed | AY0033018835-01 | 2024-10-14 10:42 | 2024-10-14 13:02 | No | 1
QF01160866996 | CLOUDS HILL ROAD | ST GEORGE | 4545035 | Footway, Carriageway | Approximately from the corner of Church Road and Clouds Hill Road to the corner of Clouds Hill Avenue | BRISTOL CITY COUNCIL | 2024-12-17 | 2024-12-17 | 1 Working days. 1 Calendar days | Highway improvement works | Retrofit - Traffic signals pole and equipment replacement | Minor | Multi-way signals | No | Works completed | QF01160866996-01 | 2024-12-17 09:30 | 2024-12-17 14:00 | No | 1
LN0782493272 | CLOUDS HILL ROAD | ST GEORGE | 4545035 | Footway | o/s 51 | National Grid Electricity Distribution (South West) | 2025-03-28 | 2025-04-02 | 4 Working days. 6 Calendar days | Disconnection or alteration of supply | 1 joint hole in tarmac footway for supply alteration | Standard | Some carriageway incursion | No | Works completed | LN0782493272-01 | 2025-03-28 08:24 | 2025-04-02 09:12 | No | 4
QF00596411734 | CLOUDS HILL ROAD | ST GEORGE | 4545035 | Carriageway | From number 383 to outside Summerhill Infant School | BRISTOL CITY COUNCIL | 2025-03-29 | 2025-03-30 | 0 Working days. 2 Calendar days | Highway repair and maintenance works | CAT2 Pothole repairs | Minor | Road closure | No | Works completed | QF00596411734-01 | 2025-03-29 08:00 | 2025-03-30 17:00 | No | 0
LN0142497725 | CLOUDS HILL ROAD | ST GEORGE | 4545035 | Footway | OUTSIDE 97 | National Grid Electricity Distribution (South West) | 2025-04-02 | 2025-04-08 | 5 Working days. 7 Calendar days | Utility repair and maintenance works | Urgent excavation in highway to locate and repair LV cable fault. | Immediate - urgent | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | LN0142497725-01 | 2025-04-02 11:45 | 2025-04-08 19:09 | No | 5
AY0093041350 | CLOUDS HILL ROAD | ST GEORGE | 4545035 | Footway | From outside 117 to outside 137 | BRISTOL WATERWORKS COMPANY | 2025-04-10 | 2025-04-11 | 2 Working days. 2 Calendar days | Utility repair and maintenance works | replace leaking stop tap 500lph | Immediate - urgent | Two-way signals | Yes, a pedestrian walkway will be provided | Works completed | AY0093041350-01 | 2025-04-10 09:30 | 2025-04-11 15:45 | No | 2
LN0142499030 | CLOUDS HILL ROAD | ST GEORGE | 4545035 | Footway, Carriageway | Outside 155 | National Grid Electricity Distribution (South West) | 2025-04-14 | 2025-04-22 | 5 Working days. 9 Calendar days | Utility repair and maintenance works | Urgent excavation in highway to locate and repair HV cable fault. | Immediate - urgent | Multi-way signals | Yes, a pedestrian walkway will be provided | Works completed | LN0142499030-01 | 2025-04-14 09:50 | 2025-04-22 17:40 | No | 5
AY0093044470 | CLOUDS HILL ROAD | ST GEORGE | 4545035 | Footway | Outside no.64 | BRISTOL WATERWORKS COMPANY | 2025-05-09 | 2025-05-13 | 3 Working days. 5 Calendar days | Utility repair and maintenance works | REPLACE LEAKING STOP TAP | Minor | Some carriageway incursion | No | Works completed | AY0093044470-01 | 2025-05-09 10:19 | 2025-05-13 17:00 | No | 3
AY0093044498 | CLOUDS HILL ROAD | ST GEORGE | 4545035 | Footway | O/S 47 | BRISTOL WATERWORKS COMPANY | 2025-05-09 | 2025-05-14 | 4 Working days. 6 Calendar days | Utility repair and maintenance works | REPLACE LEAKING STOP TAP X2 | Standard | Some carriageway incursion | Yes, an alternative route will be provided | Works completed | AY0093044498-01 | 2025-05-09 10:58 | 2025-05-14 14:25 | No | 4
XY212004000193637 | CLOUDS HILL ROAD | ST GEORGE | 4545035 | Footway, Carriageway | LIGHTS IN USE FROM O/S 44 TO O/S 43 | WALES AND WEST UTILITIES LTD | 2025-05-18 | 2025-05-18 | 0 Working days. 1 Calendar days | Utility repair and maintenance works | LAYING NEW SERVICE 7M PUBLIC | Minor | Two-way signals | Yes, a pedestrian walkway will be provided | Works completed | XY212004000193637-03 | 2025-05-18 07:22 | 2025-05-18 08:35 | No | 0
AY0093041351 | CLOUDS HILL ROAD | ST GEORGE | 4545035 | Footway | From 72 - 86 | BRISTOL WATERWORKS COMPANY | 2025-06-26 | 2025-06-27 | 1 Working days. 1 Calendar days | Utility repair and maintenance works | Repair leaking stoptap - Losing 120lph | Minor | Two-way signals | Yes, a pedestrian walkway will be provided | Works completed | AY0093041351-02 | 2025-06-26 08:44 | 2025-06-26 09:20 | No | 1
AY0093091073 | CLOUDS HILL ROAD | ST GEORGE | 4545035 | Footway, Carriageway | From 47 to 55 | BRISTOL WATERWORKS COMPANY | 2025-08-18 | 2025-08-27 | 7 Working days. 10 Calendar days | Utility repair and maintenance works | x3 New water connections with cut off in the same trench | Standard | No carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | AY0093091073-01 | 2025-08-18 11:29 | 2025-08-27 08:24 | No | 7
QF00501696908 | CLOUDS HILL ROAD | ST GEORGE | 4545035 | Carriageway | No. 1 to Summerhill Road junction | BRISTOL CITY COUNCIL | 2025-09-16 | 2025-09-16 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | Cat 2 defect repair - repairing pothole | Minor | Multi-way signals | No | Works completed | QF00501696908-01 | 2025-09-16 10:00 | 2025-09-16 15:30 | No | 1
AY0073041351 | CLOUDS HILL ROAD | ST GEORGE | 4545035 | Footway | outside 84 | BRISTOL WATERWORKS COMPANY | 2025-09-24 | 2025-09-26 | 3 Working days. 3 Calendar days | Utility repair and maintenance works | REPAIR/REPLACE LEAKING STOPTAP OR METER | Minor | Some carriageway incursion | No | Works completed | AY0073041351-01 | 2025-09-24 11:40 | 2025-09-26 17:26 | No | 3
LN0782512994 | CLOUDS HILL ROAD | ST GEORGE | 4545035 | Footway | outside 96 | National Grid Electricity Distribution (South West) | 2025-10-06 | 2025-10-09 | 4 Working days. 4 Calendar days | New service connection | 2 joint holes in tarmac footway for new supply, disconnection of supply | Standard | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | LN0782512994-01 | 2025-10-06 17:00 | 2025-10-09 17:40 | No | 4
RZ11772787559 | CONHAM ROAD | ST GEORGE | 4566199 | Carriageway | Approx. 50m west of Lime Road to Lower Conham Vale | SOUTH GLOUCESTERSHIRE COUNCIL | 2024-10-22 | 2024-10-23 | 1 Working days. 1 Calendar days | Highway improvement works | Pothole repairs | Minor | Two-way signals | No | Works completed | RZ11772787559-01 | 2024-10-22 09:30 | 2024-10-22 15:30 | No | 1
BC008WG1VL10N | CONHAM ROAD | ST GEORGE | 4566199 | Footway, Carriageway | CONHAM RD BRISTOL BS4 4QA | BT | 2024-11-18 | 2024-11-19 | 2 Working days. 2 Calendar days | Utility repair and maintenance works | Urgent 2 way lights manned at all times off peak only. Overhead cable has been damaged and is dangerously low customers service affected | Immediate - urgent | Two-way signals | No | Works completed | BC008WG1VL10N-01 | 2024-11-18 13:26 | 2024-11-19 14:52 | No | 2
QF00523169792 | CREWS HOLE ROAD | ST GEORGE | 4550701 | Carriageway | From its junction with Blackswarth Road to its junction with Troopers Hill Road | BRISTOL CITY COUNCIL | 2024-12-16 | 2024-12-16 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | Wall Collapse - Spoil removal from carriageway | Minor | Road closure | No | Works completed | QF00523169792-02 | 2024-12-16 10:32 | 2024-12-16 12:54 | No | 1
AY0092956163 | CREWS HOLE ROAD | ST GEORGE | 4550701 | Footway, Carriageway | O/S Springwater Park Trading Estate | BRISTOL WATERWORKS COMPANY | 2025-02-20 | 2025-02-24 | 3 Working days. 5 Calendar days | Utility repair and maintenance works | Fire hydrant frame and cover | Minor | Some carriageway incursion | No | Works completed | AY0092956163-04 | 2025-02-20 09:10 | 2025-02-24 12:18 | No | 3
QF00431895497 | CREWS HOLE ROAD | ST GEORGE | 4550701 | Footway, Carriageway, Verge | From Strawberry Lane to Didac (Woodwise Academy) | BRISTOL CITY COUNCIL | 2025-06-16 | 2025-06-27 | 10 Working days. 12 Calendar days | Highway improvement works | Building new traffic calming areas and laybys | Major | Road closure | Yes, an alternative route will be provided | Works completed | QF00431895497-02 | 2025-06-16 08:00 | 2025-06-27 17:00 | Yes, closure has been discussed with Highway Authority | 10
LN0142486027 | DAYS ROAD | ST PHILIPS | 4542515 | Carriageway, Footpath | side of pub | National Grid Electricity Distribution (South West) | 2025-01-11 | 2025-01-17 | 5 Working days. 7 Calendar days | Utility repair and maintenance works | Urgent excavation in highway to locate and repair LV cable fault. | Immediate - urgent | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | LN0142486027-01 | 2025-01-11 19:30 | 2025-01-16 14:48 | No | 5
XY211003001778693 | FEEDER ROAD | ST PHILIPS | 4549589 | Footway, Carriageway, Footpath | O/S UNIT 18-20 - JUNC CATTLE MARKET ROAD | WALES AND WEST UTILITIES LTD | 2023-12-08 | 2025-04-04 | 334 Working days. 481 Calendar days | Utility repair and maintenance works | REPLACE 413.77M OF OLD METALLIC GAS MAINS WITH 413.77M OF NEW PLASTIC MAINS AND RENEW/TRANSFER APPROX. 3 SERVICE PIPES TO ADJACENT PREMISES. | Major | Multi-way signals | Yes, a pedestrian walkway will be provided | Works completed | XY211003001778693-02 | 2023-12-11 08:30 | 2025-04-04 17:00 | Yes, closure has been discussed with Highway Authority | 334
BC004WFMN9H2R02 | FEEDER ROAD | ST PHILIPS | 4549589 | Footway | o/s 31B FEEDER ROAD | BT | 2024-10-03 | 2024-10-07 | 2 Working days. 2 Calendar days | Utility repair and maintenance works | Maintenance excavation on the F/W to install new BT/Openreach duct. | Minor | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | BC004WFMN9H2R02-01 | 2024-10-03 13:53 | 2024-10-04 13:02 | No | 2
D201755939903 | FEEDER ROAD | ST PHILIPS | 4549589 | Carriageway | Outside Mooring Posts | Netomnia Limited | 2024-10-06 | 2024-10-06 | 0 Working days. 1 Calendar days | Optional permit (no fee) e.g. for traffic management etc | TM/SIGNAGE ONLY | Minor | Multi-way signals | No | Works completed | D201755939903-01 | 2024-10-06 09:00 | 2024-10-06 17:00 | No | 0
BC112-BWDOSAFBR28436 | FEEDER ROAD | ST PHILIPS | 4549589 | Footway | JNCT ALBERT ROAD TO O/S 13 | BT | 2024-10-28 | 2024-11-04 | 5 Working days. 6 Calendar days | Utility asset works | Excavate to lay duct and build / replace joint box/es | Standard | No carriageway incursion | No | Works completed | BC112-BWDOSAFBR28436-01 | 2024-10-28 08:30 | 2024-11-02 08:22 | No | 5
LN0122476936C | FEEDER ROAD | ST PHILIPS | 4549589 | Footway, Carriageway | Opposite 80 | National Grid Electricity Distribution (South West) | 2024-11-18 | 2025-01-31 | 52 Working days. 75 Calendar days | Utility asset works | 1 joint hole in tarmac footway and tarmac road for cable diversion and cable overlay | Major | Two-way signals | Yes, a pedestrian walkway will be provided | Works completed | LN0122476936C-02 | 2024-11-18 13:00 | 2025-01-31 16:52 | No | 52
PG10762338635001 | FEEDER ROAD | ST PHILIPS | 4549589 | Carriageway | 72-78 | WESSEX WATER | 2024-11-30 | 2024-11-30 | 0 Working days. 1 Calendar days | Utility repair and maintenance works | Section 81/Defect | Minor | Two-way signals | No | Works completed | PG10762338635001-06 | 2024-11-30 08:31 | 2024-11-30 15:00 | No | 0
NX513SW-QFS8187508170 | FEEDER ROAD | ST PHILIPS | 4549589 | Carriageway | O/s 84-87 To Entrance To Kenneth Steele House | VODAFONE GROUP | 2024-12-11 | 2024-12-12 | 2 Working days. 2 Calendar days | Remedial works | S81 Defect - QFS8187508170 - Repair carriageway chamber due to trip hazard | Immediate - urgent | Give and take | No | Works completed | NX513SW-QFS8187508170-03 | 2024-12-11 19:38 | 2024-12-12 00:41 | No | 2
KL238MLN111748070125DB | FEEDER ROAD | ST PHILIPS | 4549589 | Carriageway | Either side of the railway bridge for a distance of approx 70m from the j/w Cole Road to the advertising board | NETWORK RAIL | 2025-01-07 | 2025-01-08 | 2 Working days. 2 Calendar days | Works for Rail Purposes | Detailed Examination of railway bridge - 21:00 - 05:00 | Minor | Road closure | No | Works completed | KL238MLN111748070125DB-01 | 2025-01-07 21:00 | 2025-01-08 05:00 | No | 2
LN0782483909 | FEEDER ROAD | ST PHILIPS | 4549589 | Footway | Outside Electricity Substation, 46m west from junction of ALBERT ROAD | National Grid Electricity Distribution (South West) | 2025-01-16 | 2025-01-27 | 8 Working days. 12 Calendar days | Utility asset works | 1 joint hole in tarmac footway for substation works. | Standard | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | LN0782483909-02 | 2025-01-16 09:40 | 2025-01-27 17:38 | No | 8
LN0782483170 | FEEDER ROAD | ST PHILIPS | 4549589 | Footway | Approx 55M from Cattle Market Tavern | National Grid Electricity Distribution (South West) | 2025-02-03 | 2025-02-11 | 7 Working days. 9 Calendar days | Utility asset works | 1 joint hole in tarmac footway and 8m trenching in tarmac footway for new substation. | Standard | No carriageway incursion | No | Works completed | LN0782483170-01 | 2025-02-03 09:47 | 2025-02-11 16:38 | No | 7
XY212001004880517 | FEEDER ROAD | ST PHILIPS | 4549589 | Footway, Carriageway | O/S SIR ROBERT MCALPINE LTD, SITE OFFICE CATTLE | WALES AND WEST UTILITIES LTD | 2025-03-12 | 2025-03-20 | 7 Working days. 9 Calendar days | Utility repair and maintenance works | TRACE AND REPAIR GAS ESCAPE AND PERMANENTLY REINSTATE WHERE POSSIBLE. | Immediate - emergency | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | XY212001004880517-01 | 2025-03-12 14:16 | 2025-03-20 10:42 | No | 7
LN0782498572 | FEEDER ROAD | ST PHILIPS | 4549589 | Footway, Carriageway | Outside site entrance near junction with Cattle Market Road | National Grid Electricity Distribution (South West) | 2025-04-26 | 2025-05-02 | 5 Working days. 7 Calendar days | New service connection | 1 joint hole and 2m trenching in tarmac footway and 15m trenching in tarmac road for new supply | Standard | Give and take | Yes, an alternative route will be provided | Works completed | LN0782498572-01 | 2025-04-26 08:32 | 2025-05-02 10:03 | No | 5
LN0142500811 | FEEDER ROAD | ST PHILIPS | 4549589 | Footway, Carriageway | Outside Unite Students | National Grid Electricity Distribution (South West) | 2025-05-01 | 2025-05-09 | 2 Working days. 2 Calendar days | Utility repair and maintenance works | Urgent excavation in highway to locate and repair HV cable fault. | Immediate - urgent | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | LN0142500811-01 | 2025-05-01 11:00 | 2025-05-02 10:41 | No | 2
AY0093074011 | FEEDER ROAD | ST PHILIPS | 4549589 | Verge | o/s Unit F | BRISTOL WATERWORKS COMPANY | 2025-05-28 | 2025-05-29 | 2 Working days. 2 Calendar days | Utility repair and maintenance works | Dangerous cover repair | Minor | No carriageway incursion | No | Works completed | AY0093074011-01 | 2025-05-28 13:22 | 2025-05-29 15:02 | No | 2
QF050CM1 | FEEDER ROAD | ST PHILIPS | 4549589 | Footway | Feeder Road at entrance into new UOB site | BRISTOL CITY COUNCIL | 2025-06-19 | 2025-06-20 | 2 Working days. 2 Calendar days | New service connection | Extension of BCC BNET ducting to link with UOB ducting | Minor | No carriageway incursion | No | Works completed | QF050CM1-01 | 2025-06-19 09:00 | 2025-06-20 15:30 | No | 2
XY212001004392708 | FEEDER ROAD | ST PHILIPS | 4549589 | Footway | SOUTHERN FOOTWAY, AT THE J/O NEW BRISLINGTON BRIDGE | WALES AND WEST UTILITIES LTD | 2025-06-25 | 2025-06-25 | 1 Working days. 1 Calendar days | Remedial works | REPAIRS TO DEFECTIVE REINSTATEMENT (WWU REF:D21107) | Minor | No carriageway incursion | No | Works completed | XY212001004392708-02 | 2025-06-25 10:45 | 2025-06-25 11:12 | No | 1
NK110ANSL119820 | FEEDER ROAD | ST PHILIPS | 4549589 | Footway | OUTSIDE 82, FEEDER ROAD | VIRGIN MEDIA | 2025-07-16 | 2025-07-18 | 1 Working days. 1 Calendar days | Remedial works | REMEDIAL WORKS | Minor | Some carriageway incursion | No | Works completed | NK110ANSL119820-08 | 2025-07-17 17:00 | 2025-07-17 18:00 | No | 1
QF01121357507 | FEEDER ROAD | ST PHILIPS | 4549589 | Footway, Carriageway, Verge | Approximately 50 m from Cole Road towards west on Feeder Road | BRISTOL CITY COUNCIL | 2025-09-03 | 2025-09-05 | 3 Working days. 3 Calendar days | Highway improvement works | Retrofit and controller swap | Minor | Two-way signals | No | Works completed | QF01121357507-02 | 2025-09-03 09:30 | 2025-09-05 15:00 | No | 3
QF00522838188 | FEEDER ROAD | ST PHILIPS | 4549589 | Carriageway | For 40m eastwards starting 10m west of Netham Road junction | BRISTOL CITY COUNCIL | 2025-10-16 | 2025-10-16 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | Cat 2 defect repair - repairing pothole | Minor | Multi-way signals | No | Works in progress | QF00522838188-01 | 2025-10-16 12:00 |  | No | 1
QF01251525343 | FIRECLAY ROAD | ST GEORGE | 4582463 | Carriageway | Entire length of Fireclay Road | BRISTOL CITY COUNCIL | 2025-03-02 | 2025-03-02 | 0 Working days. 1 Calendar days | Highway repair and maintenance works | Pothole repair and surfacing | Minor | Road closure | No | Works completed | QF01251525343-01 | 2025-03-02 08:00 | 2025-03-02 17:00 | No | 0
QF00504040802 | FIRECLAY ROAD | ST GEORGE | 4582463 | Carriageway | From its junction with Blackswarth Road to its junction with Netham Road | BRISTOL CITY COUNCIL | 2025-05-11 | 2025-05-11 | 0 Working days. 1 Calendar days | Statutory Infrastructure Works | Surface dressing (SD) | Minor | Road closure | No | Works completed | QF00504040802-01 | 2025-05-11 08:00 | 2025-05-11 18:00 | No | 0
QF00594787079 | FIRECLAY ROAD | ST GEORGE | 4582463 | Carriageway | From its junction with Blackswarth Road to its junction with Netham Road | BRISTOL CITY COUNCIL | 2025-05-18 | 2025-05-18 | 0 Working days. 1 Calendar days | Statutory Infrastructure Works | Lockdown/Lockchip (LD/LC) | Minor | Road closure | No | Works planned | QF00594787079-01 | 2025-05-18 08:00 | 2025-05-18 18:00 | No | 0
QF01148254659 | LAWRENCE HILL | LAWRENCE HILL | 4530482 | Footway, Carriageway | Approximately from 180 to 206 Lawrence Hill | BRISTOL CITY COUNCIL | 2025-01-14 | 2025-01-14 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | Retrofit - Traffic signal head replacement | Minor | Multi-way signals | No | Works completed | QF01148254659-02 | 2025-01-14 09:30 | 2025-01-14 15:30 | No | 1
BC008FAA6088MCR0AR5A | LAWRENCE HILL | LAWRENCE HILL | 4530482 | Footway | Working from south of Lawrence hill roundabout to Clarence Road | BT | 2025-02-17 | 2025-02-20 | 9 Working days. 11 Calendar days | Utility asset works | Access to Openreach underground equipment. Night working | Standard | No carriageway incursion | No | Works completed | BC008FAA6088MCR0AR5A-01 | 2025-02-17 17:54 | 2025-02-27 09:15 | No | 9
ZH00113903166 | LAWRENCE HILL | LAWRENCE HILL | 4530482 | Footway, Carriageway | 1102-1081 - From Jcn Sarah Street to approach of Lawrence Hill Roundabout | NWP STREET LTD (formerly New World Payphones Ltd) | 2025-03-10 | 2025-03-11 | 1 Working days. 1 Calendar days | Highway improvement works | Bus Shelter Deconversion - Ad to Non-Ad | Minor | Lane closure | No | Works completed | ZH00113903166-03 | 2025-03-10 12:20 | 2025-03-10 16:00 | No | 1
QF00668247510 | LAWRENCE HILL | LAWRENCE HILL | 4530482 | Carriageway | Inbound, from access into subway to o/s no. 1. | BRISTOL CITY COUNCIL | 2025-03-10 | 2025-03-15 | 5 Working days. 6 Calendar days | Works for road purposes | Drainage survey for up-coming highway improvement scheme. | Standard | Lane closure | No | Works completed | QF00668247510-01 | 2025-03-10 20:00 | 2025-03-15 05:00 | No | 5
QF00804194549 | LAWRENCE HILL | LAWRENCE HILL | 4530482 | Footway | o/s 182-186 | BRISTOL CITY COUNCIL | 2025-03-22 | 2025-03-22 | 0 Working days. 1 Calendar days | Highway repair and maintenance works | replace damaged chamber cover | Minor | Some carriageway incursion | No | Works completed | QF00804194549-01 | 2025-03-22 09:30 | 2025-03-22 12:00 | No | 0
QF00642994991 | LAWRENCE HILL | LAWRENCE HILL | 4530482 | Carriageway | Between junction with Sarah Street to junction with Roundabout. | BRISTOL CITY COUNCIL | 2025-03-28 | 2025-04-01 | 3 Working days. 5 Calendar days | Works for road purposes | Drainage survey for up-coming highway improvement scheme. | Minor | Lane closure | No | Works completed | QF00642994991-01 | 2025-03-28 20:00 | 2025-04-01 05:00 | No | 3
AY0093042997 | LAWRENCE HILL | LAWRENCE HILL | 4530482 | Footway | from O/S 208 to 188 | BRISTOL WATERWORKS COMPANY | 2025-06-03 | 2025-06-05 | 2 Working days. 2 Calendar days | Utility repair and maintenance works | SECTION 81 | Minor | Lane closure | No | Works completed | AY0093042997-01 | 2025-06-03 09:57 | 2025-06-04 16:35 | No | 2
LN0772502358 | LAWRENCE HILL | LAWRENCE HILL | 4530482 | Footway | Outside 188 | National Grid Electricity Distribution (South West) | 2025-06-16 | 2025-06-19 | 4 Working days. 4 Calendar days | New service connection | 1 joint hole in tarmac footway for new supply | Standard | Some carriageway incursion | No | Works completed | LN0772502358-01 | 2025-06-16 13:40 | 2025-06-19 10:45 | No | 4
NK110ANSL240029 | LAWRENCE HILL | LAWRENCE HILL | 4530482 | Footway | outside 141 LAWRENCE HILL BRISTOL BS5 0BT | VIRGIN MEDIA | 2025-08-21 | 2025-08-22 | 1 Working days. 1 Calendar days | Utility asset works | INSTALL TEE IN FOOTWAY (NEW CUSTOMER CONNECTION) | Minor | No carriageway incursion | Yes, an alternative route will be provided | Works completed | NK110ANSL240029-01 | 2025-08-21 10:26 | 2025-08-21 17:00 | No | 1
QF00574807884 | LAWRENCE HILL | LAWRENCE HILL | 4530482 | Carriageway | 212 to 210 | BRISTOL CITY COUNCIL | 2025-10-07 | 2025-10-07 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | Cat 2 defect repair - repairing pothole | Minor | Lane closure | No | Works completed | QF00574807884-02 | 2025-10-07 09:30 | 2025-10-07 15:30 | No | 1
QF00879083665 | LAWRENCE HILL ROUNDABOUT | EASTON | 4530484 | Carriageway | from opp j/o Easton Road, continuing north for approx. 130mtrs. | BRISTOL CITY COUNCIL | 2024-11-14 | 2024-11-14 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | TM to assist with column replacement | Minor | Lane closure | No | Works completed | QF00879083665-01 | 2024-11-14 10:00 | 2024-11-14 14:30 | No | 1
QF01179539019 | LAWRENCE HILL ROUNDABOUT | EASTON | 4530484 | Footway, Carriageway | Approximately from the exit of Clarence Road to Easton Way on Lawrence Hill Roundabout | BRISTOL CITY COUNCIL | 2025-07-17 | 2025-07-18 | 2 Working days. 2 Calendar days | Highway repair and maintenance works | Traffic lamp (aspect) change on 6 m pole | Minor | Lane closure | No | Works completed | QF01179539019-01 | 2025-07-17 19:00 | 2025-07-18 03:00 | No | 2
QF00444222385 | MARSH LANE | ST PHILIPS | 4545211 | Footway, Carriageway | From Avonvale Road jct to Glendare Street jct | BRISTOL CITY COUNCIL | 2024-11-14 | 2024-11-18 | 3 Working days. 5 Calendar days | Highway improvement works | Installation of planters and bus gate to restrict vehicle access. Applying thermoplastic ground markings | Minor | Road closure | Yes, an alternative route will be provided | Works completed | QF00444222385-01 | 2024-11-14 09:00 | 2024-11-18 15:50 | No | 3
BC01001179558499 | MARSH LANE | ST PHILIPS | 4545211 | Footway | 25m south from Granville St Junction | BT | 2024-11-22 | 2024-11-26 | 1 Working days. 1 Calendar days | Utility asset works | Remove BT kiosk | Minor | Some carriageway incursion | No | Works completed | BC01001179558499-05 | 2024-11-21 13:06 | 2024-11-21 14:10 | No | 1
LN0142481634B | MARSH LANE | ST PHILIPS | 4545211 | Footway, Carriageway | To the side 185 Avondale | National Grid Electricity Distribution (South West) | 2024-11-28 | 2024-12-04 | 5 Working days. 7 Calendar days | Utility repair and maintenance works | Urgent excavation in highway to locate and repair LV cable fault. | Immediate - urgent | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | LN0142481634B-01 | 2024-11-28 10:00 | 2024-12-04 10:02 | No | 5
AY0093110779 | MARSH LANE | ST PHILIPS | 4545211 | Footway | O/s 185 Avondale Road | BRISTOL WATERWORKS COMPANY | 2025-08-29 | 2025-09-04 | 5 Working days. 7 Calendar days | Utility repair and maintenance works | Replace leaking air valve, 30,000LPH | Immediate - urgent | No carriageway incursion | No | Works completed | AY0093110779-01 | 2025-08-29 10:04 | 2025-09-04 13:35 | No | 5
AY0093115954 | MARSH LANE | ST PHILIPS | 4545211 | Footway | Side of 185 Avondale Road | BRISTOL WATERWORKS COMPANY | 2025-09-16 | 2025-09-18 | 3 Working days. 3 Calendar days | Utility repair and maintenance works | Burst main | Minor | No carriageway incursion | No | Works completed | AY0093115954-01 | 2025-09-16 09:59 | 2025-09-18 19:50 | No | 3
BC004WFSVP10B | MORLEY STREET | REDFIELD | 4571072 | Footway | O/S ROWAN COURT, MORLEY STREET , BARTON HILL , BRISTOL BS5 9LY | BT | 2024-11-18 | 2024-11-20 | 1 Working days. 1 Calendar days | Utility repair and maintenance works | Maintenance dig required to expose a buried joint and provide service maybe new cable or duct to property. Also try to attempt to install a BT/Openreach chamber with frame and cover on joint. | Minor | Some carriageway incursion | Yes, an alternative route will be provided | Works completed | BC004WFSVP10B-01 | 2024-11-18 11:27 | 2024-11-18 11:35 | No | 1
D201739891167 | MORLEY STREET | ST WERBURGHS | 4536158 | Footway | Outside of 11 - 17 | Netomnia Limited | 2024-11-20 | 2024-11-25 | 2 Working days. 2 Calendar days | Utility asset works | Overlay required | Minor | Give and take | Yes, an alternative route will be provided | Works completed | D201739891167-01 | 2024-11-21 17:30 | 2024-11-22 16:40 | No | 2
BC008FAA6088MCR0AR2 | MORLEY STREET | REDFIELD | 4571072 | Footway | Working from corner of Cobden Street to corner of Ducie Road | BT | 2025-02-17 | 2025-02-20 | 4 Working days. 4 Calendar days | Utility asset works | Access to Openreach underground equipment. Night working | Standard | No carriageway incursion | No | Works completed | BC008FAA6088MCR0AR2-02 | 2025-02-17 16:15 | 2025-02-20 06:30 | No | 4
QF00405529895 | PILEMARSH | ST GEORGE | 4528591 | Footway, Carriageway | From Avonvale Road junction to Netham Road junction | BRISTOL CITY COUNCIL | 2024-11-11 | 2024-11-13 | 3 Working days. 3 Calendar days | Highway improvement works | Installation of bus gate to restrict vehicle access | Minor | Road closure | No | Works completed | QF00405529895-01 | 2024-11-11 09:00 | 2024-11-13 15:30 | No | 3
XY212001004969738 | PILEMARSH | ST GEORGE | 4528591 | Footway, Carriageway | O/S 56 | WALES AND WEST UTILITIES LTD | 2025-06-11 | 2025-06-18 | 6 Working days. 8 Calendar days | Utility repair and maintenance works | TRACE AND REPAIR GAS ESCAPE AND PERMANENTLY REINSTATE WHERE POSSIBLE. | Immediate - emergency | Some carriageway incursion | Yes, an alternative route will be provided | Works completed | XY212001004969738-01 | 2025-06-11 18:26 | 2025-06-18 13:17 | No | 6
XY207001005010639 | REAR ACCESS TROOPERS HILL ROAD | ST GEORGE | 4518129 | Footway, Carriageway | REAR OF 35 | WALES AND WEST UTILITIES LTD | 2025-08-05 | 2025-08-11 | 4 Working days. 4 Calendar days | Utility repair and maintenance works | TRACE AND REPAIR GAS ESCAPE AND PERMANENTLY REINSTATE WHERE POSSIBLE. | Immediate - emergency | Some carriageway incursion | Yes, a pedestrian walkway will be provided | Works completed | XY207001005010639-01 | 2025-08-05 15:00 | 2025-08-08 17:15 | No | 4
QF01160727216 | RUSSELL TOWN AVENUE | REDFIELD | 4573021 | Footway, Carriageway, Verge | Approximately 38 m from Church Road on Russel Town Ave towards north | BRISTOL CITY COUNCIL | 2025-02-14 | 2025-02-14 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | Retrofit - Traffic signal head replacement | Minor | Multi-way signals | No | Works completed | QF01160727216-01 | 2025-02-14 09:30 | 2025-02-14 15:30 | No | 1
QF00531057338 | RUSSELL TOWN AVENUE | REDFIELD | 4573021 | Carriageway | For 25m northwards starting 30m north of Cattybrook Street | BRISTOL CITY COUNCIL | 2025-10-02 | 2025-10-02 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | Cat 2 defect repair - repairing pothole | Minor | Two-way signals | No | Works completed | QF00531057338-01 | 2025-10-02 09:30 | 2025-10-02 15:30 | No | 1
QF00517512003 | RUSSELL TOWN AVENUE | REDFIELD | 4573021 | Carriageway | For 20m northwards, starting 5m south of Cattybrook Street | BRISTOL CITY COUNCIL | 2025-10-15 | 2025-10-15 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | Cat 2 defect repair - repairing pothole | Minor | Multi-way signals | No | Works completed | QF00517512003-01 | 2025-10-15 09:30 | 2025-10-15 15:30 | No | 1
PG101SAST008533_SR | SUMMERHILL ROAD | ST GEORGE | 4532165 | Footway, Carriageway | From O/S 120 to O/S 42 | WESSEX WATER | 2024-10-02 | 2024-10-03 | 2 Working days. 2 Calendar days | Utility repair and maintenance works | CCTV sewer survey from existing manholes to check the condition of pipe. | Minor | Lane closure | No | Works completed | PG101SAST008533_SR-01 | 2024-10-02 20:30 | 2024-10-03 04:00 | No | 2
ZH00132439778 | SUMMERHILL ROAD | ST GEORGE | 4532165 | Footway, Carriageway | From o/s 31 to o/s 85 | NWP STREET LTD (formerly New World Payphones Ltd) | 2024-12-11 | 2024-12-12 | 1 Working days. 1 Calendar days | Utility asset works | Bus Shelter Deconversion Ad to Non-ad | Minor | Contra-flow | Yes, a pedestrian walkway will be provided | Works completed | ZH00132439778-02 | 2024-12-11 09:50 | 2024-12-11 15:30 | No | 1
QF01105399474 | SUMMERHILL ROAD | ST GEORGE | 4532165 | Footway, Carriageway | Approximately from the corner of Church Road and Summerhill Road to 5 Summerhill Road | BRISTOL CITY COUNCIL | 2024-12-17 | 2024-12-17 | 1 Working days. 1 Calendar days | Highway improvement works | Retrofit - Traffic signals pole and equipment replacement | Minor | Multi-way signals | No | Works completed | QF01105399474-01 | 2024-12-17 09:30 | 2024-12-17 14:00 | No | 1
ZH00132439778 | SUMMERHILL ROAD | ST GEORGE | 4532165 | Footway | o/s Butler House & Opp 62 | NWP STREET LTD (formerly New World Payphones Ltd) | 2025-02-07 | 2025-02-08 | 1 Working days. 1 Calendar days | Remedial works | Remedial works to roof of Bus shelter | Minor | No carriageway incursion | No | Works completed | ZH00132439778-03 | 2025-02-07 09:30 | 2025-02-07 10:00 | No | 1
AY0093022573-04 | SUMMERHILL ROAD | ST GEORGE | 4532165 | Footway, Carriageway | Outside Number 109, to Outside Number 160 | BRISTOL WATERWORKS COMPANY | 2025-03-20 | 2025-03-24 | 3 Working days. 5 Calendar days | Utility repair and maintenance works | new water supply | Minor | Two-way signals | Yes, an alternative route will be provided | Works completed | AY0093022573-04-02 | 2025-03-20 09:33 | 2025-03-24 18:10 | No | 3
D201726133990 | SUMMERHILL ROAD | ST GEORGE | 4532165 | Footway | Outside 103 to outside 123 | Netomnia Limited | 2025-03-24 | 2025-03-26 | 1 Working days. 1 Calendar days | Utility asset works | Clear 4 x f/w blockages | Minor | No carriageway incursion | Yes, an alternative route will be provided | Works completed | D201726133990-01 | 2025-03-24 12:44 | 2025-03-24 13:54 | No | 1
D201716639995 | SUMMERHILL ROAD | ST GEORGE | 4532165 | Carriageway | s/o 1 Air Balloon Road | Netomnia Limited | 2025-03-31 | 2025-04-02 | 3 Working days. 3 Calendar days | Utility asset works | Clear blockage in carriageway | Minor | Temporary obstruction 15 minute delay | No | Works completed | D201716639995-01 | 2025-03-31 09:55 | 2025-04-02 10:32 | No | 3
PG10763205782001 | SUMMERHILL ROAD | ST GEORGE | 4532165 | Carriageway | From O/S 11 to O/S 13 | WESSEX WATER | 2025-05-15 | 2025-05-16 | 1 Working days. 1 Calendar days | Utility repair and maintenance works | Section 81/Defect | Minor | Stop/go boards | No | Works completed | PG10763205782001-02 | 2025-05-15 12:05 | 2025-05-15 15:45 | No | 1
LN0782501297 | SUMMERHILL ROAD | ST GEORGE | 4532165 | Footway | OUTSIDE 86 | National Grid Electricity Distribution (South West) | 2025-05-28 | 2025-06-02 | 4 Working days. 6 Calendar days | New service connection | 1 joint hole in tarmac footway and 7m trenching in tarmac footway for new supply, disconnection of supply. | Standard | Some carriageway incursion | Yes, an alternative route will be provided | Works completed | LN0782501297-01 | 2025-05-28 09:33 | 2025-06-02 12:16 | No | 4
LN0782512623 | SUMMERHILL ROAD | ST GEORGE | 4532165 | Footway | Outside 86 | National Grid Electricity Distribution (South West) | 2025-08-26 | 2025-08-29 | 4 Working days. 4 Calendar days | Disconnection or alteration of supply | 1 joint hole in tarmac footway for disconnection of supply | Standard | Some carriageway incursion | No | Works completed | LN0782512623-01 | 2025-08-26 09:30 | 2025-08-29 09:24 | No | 4
AY0093022573-04 | SUMMERHILL ROAD | ST GEORGE | 4532165 | Carriageway | Outside Number 109, to Outside Number 160 | BRISTOL WATERWORKS COMPANY | 2025-09-18 | 2025-09-18 | 1 Working days. 1 Calendar days | Permanent reinstatement | Anti skid only | Minor | Two-way signals | No | Works completed | AY0093022573-04-03 | 2025-09-18 09:40 | 2025-09-18 15:53 | No | 1
QF00466675028 | THE AVENUE | ST GEORGE | 4558378 | Footway, Carriageway | From Jubilee Road junction to no. 35 | BRISTOL CITY COUNCIL | 2024-11-05 | 2024-11-06 | 2 Working days. 2 Calendar days | Highway improvement works | Installation of planters and bollards to restrict vehicle access | Minor | Road closure | No | Works completed | QF00466675028-01 | 2024-11-05 08:00 | 2024-11-06 15:00 | No | 2
LN0142489425 | TROOPERS HILL ROAD | ST GEORGE | 4543264 | Footway | outside 63 | National Grid Electricity Distribution (South West) | 2025-02-04 | 2025-02-13 | 8 Working days. 10 Calendar days | Utility repair and maintenance works | Urgent excavation in highway to locate and repair LV cable fault. | Immediate - urgent | Give and take | Yes, a pedestrian walkway will be provided | Works completed | LN0142489425-01 | 2025-02-04 21:15 | 2025-02-13 18:12 | No | 8
QF00891095413 | TROOPERS HILL ROAD | ST GEORGE | 4543264 | Footway | o/s 61 | BRISTOL CITY COUNCIL | 2025-09-03 | 2025-09-08 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | relocate column | Minor | No carriageway incursion | Yes, an alternative route will be provided | Works completed | QF00891095413-01 | 2025-09-04 09:30 | 2025-09-04 11:00 | No | 1
AY0093025531 | VICTORIA AVENUE | REDFIELD | 4536941 | Footway, Carriageway | O/S 128 | BRISTOL WATERWORKS COMPANY | 2024-11-18 | 2024-11-22 | 5 Working days. 5 Calendar days | Utility repair and maintenance works | Lead pipe replacement & cut off | Standard | Give and take | Yes, an alternative route will be provided | Works completed | AY0093025531-01 | 2024-11-18 11:40 | 2024-11-22 17:58 | No | 5
QF00420604020 | VICTORIA AVENUE | REDFIELD | 4536941 | Carriageway | From Baden Road jct to Avonvale Road jct | BRISTOL CITY COUNCIL | 2024-11-21 | 2024-11-26 | 4 Working days. 6 Calendar days | Highway improvement works | Installation of planters and bollards to restrict vehicle access | Standard | Road closure | No | Works completed | QF00420604020-01 | 2024-11-21 08:00 | 2024-11-26 15:45 | No | 4
AY0093039890 | VICTORIA AVENUE | REDFIELD | 4536941 | Footway, Carriageway | Outside Rose Cottage | BRISTOL WATERWORKS COMPANY | 2025-01-27 | 2025-01-31 | 5 Working days. 5 Calendar days | Utility repair and maintenance works | Separation of supply | Standard | Give and take | Yes, an alternative route will be provided | Works completed | AY0093039890-01 | 2025-01-27 08:59 | 2025-01-31 18:25 | No | 5
BC008FAA6088MCR0AR1 | VICTORIA AVENUE | REDFIELD | 4536941 | Footway | Working from No. 2 to corner of Byron Street | BT | 2025-02-17 | 2025-02-20 | 4 Working days. 4 Calendar days | Utility asset works | Access to Openreach Underground Equipment. Night working | Standard | No carriageway incursion | No | Works completed | BC008FAA6088MCR0AR1-02 | 2025-02-17 16:15 | 2025-02-20 06:30 | No | 4
XY212004000192532 | VICTORIA AVENUE | REDFIELD | 4536941 | Footway, Carriageway | O/S 130 | WALES AND WEST UTILITIES LTD | 2025-02-28 | 2025-03-05 | 4 Working days. 6 Calendar days | Utility repair and maintenance works | LAYING NEW SERVICE 4M PUBLIC | Standard | Some carriageway incursion | Yes, an alternative route will be provided | Works completed | XY212004000192532-01 | 2025-02-28 11:18 | 2025-03-05 11:37 | No | 4
AY0093039485 | VICTORIA AVENUE | REDFIELD | 4536941 | Footway | Outside 41 | BRISTOL WATERWORKS COMPANY | 2025-04-07 | 2025-04-09 | 3 Working days. 3 Calendar days | Utility repair and maintenance works | Repair leaking stop tap - 275lph | Minor | Some carriageway incursion | Yes, an alternative route will be provided | Works completed | AY0093039485-05 | 2025-04-07 08:18 | 2025-04-09 09:42 | No | 3
AY0033074472 | VICTORIA AVENUE | REDFIELD | 4536941 | Footway | O/S 20 | BRISTOL WATERWORKS COMPANY | 2025-04-29 | 2025-05-01 | 1 Working days. 1 Calendar days | Utility repair and maintenance works | Install stop tap and meter | Minor | Some carriageway incursion | Yes, an alternative route will be provided | Works completed | AY0033074472-01 | 2025-04-29 08:06 | 2025-04-29 10:13 | No | 1
QF00805222575 | VICTORIA AVENUE | REDFIELD | 4536941 | Footway | s/o 60 Leonard Road | BRISTOL CITY COUNCIL | 2025-07-02 | 2025-07-07 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | Replace column | Minor | Some carriageway incursion | Yes, an alternative route will be provided | Works completed | QF00805222575-02 | 2025-07-03 10:00 | 2025-07-03 10:45 | No | 1
XY212004000193881 | VICTORIA AVENUE | REDFIELD | 4536941 | Footway, Carriageway | O/S 152 | WALES AND WEST UTILITIES LTD | 2025-07-22 | 2025-07-28 | 5 Working days. 7 Calendar days | Utility repair and maintenance works | LAY NEW GAS SERVICE 4M PUBLIC | Standard | Give and take | Yes, an alternative route will be provided | Works completed | XY212004000193881-03 | 2025-07-22 10:29 | 2025-07-25 16:34 | No | 5
PG10762653823001 | WHITEHALL ROAD | REDFIELD | 4527006 | Carriageway | From O/S 275 to O/S 288 | WESSEX WATER | 2024-10-08 | 2024-10-09 | 1 Working days. 1 Calendar days | Utility repair and maintenance works | Section 81/Defect - Repair/Replace Cover & Frame | Minor | Stop/go boards | No | Works completed | PG10762653823001-02 | 2024-10-08 09:55 | 2024-10-08 13:20 | No | 1
PG101SAST008525 | WHITEHALL ROAD | REDFIELD | 4527006 | Carriageway | From O/S 36 to O/S 18 | WESSEX WATER | 2024-10-17 | 2024-10-17 | 1 Working days. 1 Calendar days | Utility repair and maintenance works | CCTV sewer survey from existing manholes to check the condition of pipe | Minor | Multi-way signals | No | Works completed | PG101SAST008525-02 | 2024-10-17 10:03 | 2024-10-17 12:02 | No | 1
QF01102027400 | WHITEHALL ROAD | REDFIELD | 4527006 | Carriageway | Approximately between 279 and 332 Whitehall Road | BRISTOL CITY COUNCIL | 2024-10-24 | 2024-10-24 | 1 Working days. 1 Calendar days | Highway repair and maintenance works | Traffic signal detection and repair on the road | Minor | Multi-way signals | No | Works completed | QF01102027400-01 | 2024-10-24 18:00 | 2024-10-24 23:00 | No | 1
D201761432951 | WHITEHALL ROAD | REDFIELD | 4527006 | Footway, Carriageway | From o/s 22 to o/s 94 & o/s 87 to o/s 51 | Netomnia Limited | 2025-03-10 | 2025-03-12 | 3 Working days. 3 Calendar days | Utility asset works | Clear 4 x footway blockages & 1 x carriageway blockage. Outside of 22, 51 and 53 in footway, outside 77 in carriageway | Minor | Multi-way signals | Yes, an alternative route will be provided | Works completed | D201761432951-02 | 2025-03-10 09:34 | 2025-03-12 09:30 | No | 3
D201761432951 | WHITEHALL ROAD | REDFIELD | 4527006 | Carriageway | o/s 79 to o/s 82 | Netomnia Limited | 2025-03-13 | 2025-03-13 | 1 Working days. 1 Calendar days | Permanent reinstatement | Permanent reinstatement | Minor | Stop/go boards | No | Works completed | D201761432951-03 | 2025-03-13 09:30 | 2025-03-13 10:35 | No | 1
NK110ANSL227067 | WHITEHALL ROAD | REDFIELD | 4527006 | Footway | OUTSIDE 366 WHITEHALL ROAD BRISTOL BS5 7BT | VIRGIN MEDIA | 2025-03-18 | 2025-03-19 | 1 Working days. 1 Calendar days | Utility asset works | CLEAR BLOCKED TEE IN FOOTWAY (NEW CUSTOMER CONNECTION) | Minor | Some carriageway incursion | No | Works completed | NK110ANSL227067-01 | 2025-03-19 11:25 | 2025-03-19 12:50 | No | 1
PG101SAST008953NR | WHITEHALL ROAD | REDFIELD | 4527006 | Carriageway | From O/S 235 to O/S 252 | WESSEX WATER | 2025-04-10 | 2025-04-11 | 1 Working days. 1 Calendar days | Utility repair and maintenance works | Works to enable the Manhole Survey one manhole of the network which is to assist in preventing flooding and Loss of Service | Minor | Multi-way signals | No | Works completed | PG101SAST008953NR-01 | 2025-04-11 19:45 | 2025-04-11 23:45 | No | 1
RT05051276-BLADE-MH | WHITEHALL ROAD | REDFIELD | 4527006 | Carriageway | Outside 74 Whitehall Road to 82 Whitehall Road | LUMEN TECHNOLOGIES INC | 2025-05-12 | 2025-05-14 | 3 Working days. 3 Calendar days | Utility repair and maintenance works | Essential telecoms maintenance works to repair duct located in c/w and make new connection. | Minor | Two-way signals | No | Works completed | RT05051276-BLADE-MH-03 | 2025-05-12 09:30 | 2025-05-14 12:30 | No | 3
BC008OGEA169301953WSB | WHITEHALL ROAD | REDFIELD | 4527006 | Carriageway | From outside 275 to outside 322 Whitehall Road Bristol BS5 7BW | BT | 2025-05-18 | 2025-05-18 | 0 Working days. 1 Calendar days | Utility asset works | safe access required to overhead network for engineers to provide service to a customer. 3 way lights. 1 working day 09:30 - 15:30 ** No Excavation ** | Minor | Multi-way signals | Yes, an alternative route will be provided | Works completed | BC008OGEA169301953WSB-02 | 2025-05-18 11:12 | 2025-05-18 14:20 | No | 0
RT05093319838 | WHITEHALL ROAD | REDFIELD | 4527006 | Carriageway | Whitehall Rd opp junction Foxcroft Rd | LUMEN TECHNOLOGIES INC | 2025-05-27 | 2025-05-28 | 2 Working days. 2 Calendar days | Utility asset works | Connect im of new duct to existing c/way chamber | Minor | Some carriageway incursion | No | Works planned | RT05093319838-01 | 2025-05-27 12:00 | 2025-05-28 12:27 | No | 2
BC412-BWDOSA-A-WG0F4T7X | WHITEHALL ROAD | REDFIELD | 4527006 | Footway | o/s 84 to o/s 86 | BT | 2025-06-30 | 2025-06-30 | 1 Working days. 1 Calendar days | Utility asset works | works to replace cover and frame | Minor | Some carriageway incursion | Yes, an alternative route will be provided | Works completed | BC412-BWDOSA-A-WG0F4T7X-01 | 2025-06-30 10:53 | 2025-06-30 14:51 | No | 1
RT05093319838 | WHITEHALL ROAD | REDFIELD | 4527006 | Carriageway | Whitehall Rd opp junction Foxcroft Rd | LUMEN TECHNOLOGIES INC | 2025-07-10 | 2025-07-10 | 1 Working days. 1 Calendar days | Utility asset works | Access C/Way chamber to carry out splicing works | Minor | Some carriageway incursion | No | Works planned | RT05093319838-02 | 2025-07-10 09:30 | 2025-07-10 17:30 | No | 1
PG101SAST010347WR | WHITEHALL ROAD | REDFIELD | 4527006 | Carriageway | From Junct with Canon Street to O/S 67 | WESSEX WATER | 2025-08-08 | 2025-08-09 | 1 Working days. 2 Calendar days | Utility repair and maintenance works | Works to enable the Manhole Survey one manhole of the network which is to assist in preventing flooding and Loss of Service | Minor | Road closure | No | Works completed | PG101SAST010347WR-02 | 2025-08-08 01:00 | 2025-08-09 05:00 | No | 1
AY0073051153 | WHITEHALL ROAD | REDFIELD | 4527006 | Footway | outside 435 | BRISTOL WATERWORKS COMPANY | 2025-09-25 | 2025-09-29 | 3 Working days. 5 Calendar days | Utility repair and maintenance works | REPAIR/REPLACE LEAKING STOPTAP OR METER | Minor | No carriageway incursion | No | Works completed | AY0073051153-01 | 2025-09-25 08:32 | 2025-09-29 19:53 | No | 3
AY0073045188 | WHITEHALL ROAD | REDFIELD | 4527006 | Footway | outside 232A | BRISTOL WATERWORKS COMPANY | 2025-09-25 | 2025-09-29 | 3 Working days. 5 Calendar days | Utility repair and maintenance works | REPAIR/REPLACE LEAKING STOPTAP OR METER | Minor | No carriageway incursion | No | Works completed | AY0073045188-01 | 2025-09-25 13:17 | 2025-09-29 18:23 | No | 3