## Action Plan
Action | Ref | Category | Details | Purpose/Impact | Priority | Owner | Progress/Comments | Current Status (To Do/Pending)
Review/update/reiterate SAR (Subject Access Request) roles and responsibilities across the Council | 1.1 | Procedural | Ensure the responsibility for handling requests is understood by all levels, the function is clearly delegated to key staff, and the expectations about timeliness are clearly communicated. | Compliance with SAR is an organisational commitment, and requires involvement from all areas of the Council. Improvement will only be possible if the clear roles and responsibilities in relation to compliance are established and maintained throughout the organisation. | High | Executive Office | This has been re-iterated to Exec Directors by the Chief Executive around the requirements to respond to FoIs. They have been tasked to ensure their service areas that are required to respond to requests are adequately resourced to do so, with support from the Central Disclosures Team. | Complete
Reiterate senior support and commitment to SAR compliance | 1.2 | Organisational | Identify ways in which senior management can promote a culture of adherence to SAR requirements, ensuring it is recognised as a core function within all services, and especially in services who receive a high proportion of requests. | In order for the Council to comply with requests on-time, especially in circumstances of reduced resource across the organisation, the importance of SAR compliance alongside other work needs to be embedded within the culture of the organisation. This can only happen with strong support from senior leadership, which is cascaded down through each service area. | High | Executive Office | Chief Executive has re-iterated their support of the Act and the requirement for the Council to meet its compliance obligations. Executive Directors are responsible for monitoring and reporting to Chief Executive on their service areas performance. | Complete
Review available resource and resource allocation for SAR compliance across the Council | 1.3 | Procedural | Explore whether it is possible to assign further staff to request handling in the short term, to work through backlogs of requests, where they exist. | Workload/lack of resource in some services has been highlighted as the primary cause for poor timeliness performance. Additional resource will better enable service areas to clear backlogs of requests that have accumulated and therefore improve compliance rates for new requests. | High | Service Areas | Central Disclosures Team has increased resource (via Fixed Term Contracts) to deal with the backlog. Service areas are required to monitor their volumes of request and how their service area is performing in terms of compliance. . This is to ensure that the Service are always adequality resourced. | Ongoing (no target date as this is a constant process)
Increased visibility of Central Disclosures Team and better understanding of role in SAR compliance | 1.4 | Organisational | There is inconsistency in how aware the wider organisation is of the central team and what role they play in SAR compliance. As the main support channel for the organisation, a lack of awareness of the central team harms BCC's ability to respond to SAR requests effectively. | Increased visibility, i.e.. via DMTs, on the Source, etc, will keep SAR compliance near the forefront of the organisation's thinking, and will better enable those tasked with case handling to obtain training and support. | High | Disclosures Team | The Disclosures Team have stepped up the level of engagement with Directorates, and delivering training sessions. This positive engagement can be measured by the increase in support requests and service areas proactively asking for training. The Disclosures Team have received positive feedback from across the Council in regards to the support that they have provided. | Complete
Review and update triage stage of SAR process | 1.5 | Procedural | Review triage process to identify where burden on the organisation can be reduced at an early stage, and ensure that requests are being directed to the correct service area in a timely manner. | The Council receives on average 4 requests for every day of the year. Where possible the triage stage should address requests at the point of receipt, and ensure that adequate processes are in place to get the request to the relevant service area in time. In instances where requests are not clear, clarification is sought from the data subject so that the Council can concentrate on providing information which is useful to the data subject. This will reduce the burden on the organisation, ensure that the service who will issue the response have the maximum time possible to comply with the request and that the data subject receives information most relevant to their request. | Medium | Disclosures Team | The Disclosures Team are targeted to triage requests by the working day after they are received. There is an escalation process within the team where the triaging officers are able to seek guidance on where the request needs to sit. | Complete
Update reporting resource to make service-level performance and trends clearer to senior management | 1.6 | Organisational | In order for meaningful action to be taken in relation to SAR compliance, senior leadership need to be provided with meaningful data in a timely way and which allows for immediate action. Reporting lines already exist, however the data currently presented could be improved to better show key problem areas and trends over time. | A better understanding of where issues exist and associated trends will allow senior leadership to take necessary steps earlier and more effectively, and will avoid the gradual decline in compliance which the Council has seen over the last two years. | Medium | Disclosures Team | All Executive Assistants have been given access to, and shown how to use, the iCasework reports. These are then to be shared with Directors and Executive Directors to support performance in their area. | Complete
Review and update training and support offer - Council wide | 1.7 | Organisational | Review training and support offer to ensure staff are provided with the necessary technical and legislative skills to comply with requests correctly. This should include eLearning, in-person sessions, reference materials, routes for raising queries, and refresher training. Training material already exists, but there is more than can be done to bring it under one roof, and make it more practically useful for staff directly dealing with Subject Access Requests. | In order to respond to requests effectively, staff need to be aware of both the technical and legislative requirements SAR compliance. A strong training and support offer will enable them to carry out SAR compliance duties more confidently and efficiently, and therefore speed up the response process. | Medium | Disclosures Team | The Disclosures Team have been providing face to face training to service areas to help improve their compliance. The training includes; overview of the legislation, our requirements as an organisation, responding to a requests and exemptions. e-Learning is accessible through Learning Hub and guidance documents are available on the Council's intranet for all staff to give them a high level overview of the legislation and its requirements. Services are able to access expert support from the Disclosures Team in regards to specific cases they are working on. | Complete
Review and update training and support offer - Disclosures Team | 1.8 | Organisational | As well as receiving the same training offered Council wide, Disclosures Officers receive bespoke training assist them in their role of interpreting and redacting sensitive information relating to SARs. | Each Disclosures Officer starts by working on their first request with on the job support from a Lead Disclosures Officer. This involves taking them through the case step by step until completion and providing feedback throughout this time. An instruction document has also been produced which details how to process a request from start to finish. Two meetings are held each week, where all Disclosures Officers can attend along with Lead Disclosures Officers and the Disclosures Manager. These meetings allow Disclosures Officers to discuss any issues they are having with requests and share best practice amongst the team. Support is available outside of these meetings through Teams calls and email. | Medium | Disclosures Team | Although these processes have been in place since 2023, the appointment of new staff has shown how important bespoke training for the Disclosures Officers is. The new starters have taken to their roles very well. | Complete
Review existing approach to redaction across the organisation | 1.9 | Technical | At present, each service area is responsible for carrying out its own redactions, and the tools necessary to securely redact data (i.e. Acrobat Pro) have to be sourced at a service level. This may not be the most efficient approach and should be reviewed. | A factor in delays can include the time it takes for a staff member to obtain an Acrobat Pro licence and be shown how to use the software, especially in teams which receive a relatively small number of FOIs a year. A more efficient approach to redaction should reduce the instances of such delays. | Low | Disclosures Team | The Disclosures Team offer support on how to use the current redaction software, and what should be redacted. The team are exploring new technologies as they become available to see if there is any improvements that can be made to redaction. | Ongoing (no target date as this is a constant process)
Provide clarity on the handling of 'multi-service' requests | 2 | Procedural | The current policy for case handling is that whoever holds the majority of the requested information is responsible for co-ordinating the response on behalf of BCC. This can lead to confusion or disagreement over ownership, as the ID of who holds the majority of information will not always be clear from the outset. It can also cause confusion as the policy for where responsibility lies is not always understood/accepted by the wider organisation. | An improved approach to multi-service requests will enable better timeliness in issuing a response, as time is not wasted trying to identify an owner or dealing with confusion over what the various roles/responsibilities are. | Medium | Disclosures Team | This has previously been a significant issue for the Council. Where a request is overly complex or large numbers of service areas, this is held centrally by the Disclosures Team. | Complete
Provide targeted support by Central Disclosures Team for poor performing areas | 2.1 | Procedural | Each area is currently responsible for their own compliance. The role of IG has been to report on compliance, but there has been limited intervention in areas which display consistently poor performance. The lack of an independent quasi-external presence to promote good practice can let poor performance take root. | Identifying areas with poor performance and then taking targeted steps to identify the cause of issues and possible solutions will help improve overall performance. | High | Disclosures Team | The Disclosures Team look to pro-actively monitor compliance and identify service areas that are underperforming, or where individual cases have stalled. | Ongoing (no target date as this is a constant process)
Prioritisation of SAR requests within the Central Disclosures Team | 2.2 | Procedural | New requests are prioritised based on when they are confirmed as valid requests. There is flexibility when required to prioritise urgent requests i.e. where information is needed for Court and this is done on a case by case basis. | To ensure that requests are fairly prioritised based on when the data subject has provided a clear request and confirmed their identity, if required. To allow flexibility where possible should a request need to be processed urgently, whilst ensuring this does not have a detrimental impact on existing cases. | High | Disclosures Team | The Disclosures Team prioritises older cases, but has contacted all Data Subjects to ensure expectations have been set. With fixed term additions to the team, there is flexibility to shift prioritisation to urgent requests, should this be needed. | Complete
Ongoing review of external support arrangements | 2.3 | Procedural | External support arrangements are positive, with productivity increasing from early September 2025 onwards. Larger cases are sent to the Council's external support provider to limit the time spent internally on preparation of cases. Therefore, smaller requests are deal with internally. This approach has increased productivity and this can be seen by the number of requests that have been completed over September and October 2025. | To ensure the Disclosures Team and external support used by the team is as productive as possible so that requests are responded to as quickly as possible without impacting on the quality of work. | High | Disclosures Team | Request allocation to the external support provider is now more effective with larger cases being identified to send externally. This limits the time spent internally on preparing cases and checking them before they are disclosed. Through positive conversations with the external support provider, there is a clearer understanding on how the Council expects requests to be completed and this has led to less checking and less time highlighting areas that need correcting. The Council have set monthly meetings with the external support provider to discuss any issues, but can contact the external support provider between these meetings when required. | Ongoing (no target date as this is a constant process)
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @James Martyn can we include something here around training for Dos, or maybe even as a separate line?

## Data (hidden)
1. Immediate
2. Short-Term (2023-early 2024)
3. Long-Term (mid-2024 onwards)